## Sprint Log
QuChat Mobile ¦ 10-Day Sprint Log ¦ satya.priyam@zenithstudio.live
Sprint Period: 23 Feb 2026 to 04 Mar 2026
Day | Task | Status | Upcoming / In Progress | Completed | Priority | Notes
1 | CORS fix: add capacitor://localhost to Render env var | In Progress | Update CORS_ORIGINS in Render dashboard |  | Critical | Fixes Android login rejection
1 | Verify Android login end-to-end on emulator | Upcoming | Login + send + receive message on emulator |  | Critical | Use chrome://inspect for debug
2 | Rebuild Android after CORS fix + re-sync | Upcoming | npm run build && npx cap sync android |  | High | Then click Run in Android Studio
2 | Verify Vercel production login (Render was cold-start) | Upcoming | Test with existing credentials on Vercel URL |  | High | Backend now awake — should work
3 | Safe-area polish (notch / gesture bar) | Upcoming | Apply .safe-top / .safe-bottom to Chat layout |  | High | Test on Pixel emulator
3 | Keyboard overlap fix in MessageInput | Upcoming | Wire useKeyboard hook, paddingBottom on input |  | High | Needs @capacitor/keyboard
4 | Android status bar theming | Upcoming | StatusBar.setStyle + background color in App.tsx |  | Medium | Match dark theme #0a0f1e
4 | Mobile sidebar slide-over layout | Upcoming | Drawer on mobile using use-mobile hook + Tailwind |  | High | No Ionic needed — pure CSS
5 | Touch target audit (min 44x44 px) | Upcoming | Review MessageBubble, ContactList, toolbar btns |  | Medium | Chrome DevTools mobile simulation
5 | Back-button navigation edge case testing | Upcoming | Chat -> Contacts -> exits app correctly |  | Medium | canGoBack logic in App.tsx
6 | PWA setup: vite-plugin-pwa + manifest | Upcoming | Add VitePWA() to vite.config.ts |  | High | See doc 06 for full config
6 | Create PWA icon set (72 to 512px) | Upcoming | Place in public/icons/, run Lighthouse audit |  | Medium | Target score >= 90
7 | Service worker offline caching strategy | Upcoming | CacheFirst shell, NetworkFirst API, SW media cache |  | Medium | Workbox config in vite.config.ts
7 | PWA install prompt button | Upcoming | Add InstallPWAButton.tsx to Sidebar |  | Low | beforeinstallprompt event
8 | Android release build: keystore generation | Upcoming | keytool -genkey, configure build.gradle signing |  | High | NEVER commit keystore to git
8 | Version code + Play Store prep | Upcoming | versionCode=1, versionName=1.0.0 in build.gradle |  | Medium | Need Google Play Dev account (5)
9 | End-to-end test on physical Android device | Upcoming | Login, message, media upload, back btn, resume |  | Critical | USB debug + adb install release apk
9 | Performance check on long message list | Upcoming | Load 200+ messages, observe scroll FPS |  | Medium | Add virtual scroll if janky
10 | Sprint review and documentation update | Upcoming | Update app-development-docs/ with actual findings |  | Low | Note deviations from original plan
10 | Push feature/mobile-capacitor and create PR to main | Upcoming | git push + GitHub PR with test screenshots |  | High | Triggers Render auto-redeploy
Legend: Critical (red) = drop everything ¦ High (yellow) = do today ¦ Medium (green) = this sprint ¦ Low (blue) = nice to have